## Project Schedule Creation
| Project Name: | Enviro 365 e-commerce platform
| Target Date: | July 2024
| Start Date: | 2024-04-01
| Duration: | 3 months
PROJECT SCHEDULE CREATION | [9 empty] | WEEK ONE |  |  |  |  | WEEK TWO |  |  |  |  | WEEK THREE |  |  |  |  | WEEK FOUR |  |  |  |  | WEEK FIVE |  |  |  |  | WEEK SIX |  |  |  |  | WEEK SEVEN |  |  |  |  | WEEK EIGHT |  |  |  |  | WEEK NINE |  |  |  |  | WEEK TEN |  |  |  |  | WEEK ELEVEN |  |  |  |  | WEEK TWELVE |  |  |  |  | WEEK THIRTEEN |  |  |  |  | WEEK FOURTEEN
NUM | CHATEGORY | PHASE DURATION | TASK | SUB-TASK | TASK DURATION | START DATE | FINISH DATE | TASK OWNER | DEPENDENCIES | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-22 | 2024-04-23 | 2024-04-24 | 2024-04-25 | 2024-04-26 | 2024-04-29 | 2024-04-30 | 2024-05-01 | 2024-05-02 | 2024-05-03 | 2024-05-06 | 2024-05-07 | 2024-05-08 | 2024-05-09 | 2024-05-10 | 2024-05-13 | 2024-05-14 | 2024-05-15 | 2024-05-16 | 2024-05-17 | 2024-05-20 | 2024-05-21 | 2024-05-22 | 2024-05-23 | 2024-05-24 | 2024-05-27 | 2024-05-28 | 2024-05-29 | 2024-05-30 | 2024-05-31 | 2024-06-03 | 2024-06-04 | 2024-06-05 | 2024-06-06 | 2024-06-07 | 2024-06-10 | 2024-06-11 | 2024-06-12 | 2024-06-13 | 2024-06-14 | 2024-06-17 | 2024-06-18 | 2024-06-19 | 2024-06-20 | 2024-06-21 | 2024-06-24 | 2024-06-25 | 2024-06-26 | 2024-06-27 | 2024-06-28 | 2024-07-01 | 2024-07-02 | 2024-07-03 | 2024-07-04 | 2024-07-05
A | ANALYSIS | 5 days | Requirements Gathering | Kick off meeting with stakeholders | 1 day | 2024-04-01 | 2024-04-01 | PM | 0
|  |  |  | BRS documentation | 2 days | 2024-04-02 | 2024-04-03 | BA
|  |  |  | SRS doumentation | 2 days | 2024-04-02 | 2024-04-03 | SA
|  |  |  | Scope statement definition | 2 days | 2024-04-02 | 2024-04-03 | PM
|  |  |  | Project logging | 3 days | 2024-04-01 | 2024-04-03 | PM
|  |  | Stakeholder Walkthrough | BRS walkthrough | 1 day | 2024-04-04 | 2024-04-04 | BA
|  |  |  | SRS walkthrough | 1 day | 2024-04-04 | 2024-04-04 | SA
|  |  |  | Scope statement walkthrough | 1 day | 2024-04-04 | 2024-04-04 | PM
|  |  |  | Document(s) Revision | 2 days | 2024-04-04 | 2024-04-05 | All
|  |  | Stakeholder Approval | BRS sign off | 1 day | 2024-04-05 | 2024-04-05 | BA
|  |  |  | SRS sign off | 1 day | 2024-04-05 | 2024-04-05 | SA
|  |  |  | Scope statement sign off | 1 day | 2024-04-05 | 2024-04-05 | PM
B | DESIGN | 10 days | Brainstorm | Concept brainstorm with UI/UX | 1 day | 2024-04-08 | 2024-04-08 | BA | Requirements Gathering
|  |  |  | JAD session with Dev team | 1 day | 2024-04-08 | 2024-04-08 | BA
|  |  |  | UI/UX screen design | 5 days | 2024-04-09 | 2024-04-15 | UI/UX
|  |  | Test Cases | Test case creation | 5 days | 2024-04-09 | 2024-04-15 | Testers
|  |  |  | Test case review | 1 day | 2024-04-16 | 2024-04-16 | Testers
|  |  |  | Test case sign off | 3 days | 2024-04-17 | 2024-04-19 | Testers
|  |  | RAIDs Log | Risk Matrix creation | 5 days | 2024-04-09 | 2024-04-15
|  |  | Stakeholder walkthrough | UI/UX screen design review session | 1 day | 2024-04-16 | 2024-04-16 | UI/UX
|  |  |  | UI/UX screen design revision | 2 days | 2024-04-17 | 2024-04-18 | UI/UX
|  |  |  | UI/UX screen design sign off | 1 day | 2024-04-19 | 2024-04-19 | UI/UX
C | DEVELOPMENT | 50 days | Code creation and deployment | Backend development | 20 days | 2024-04-08 | 2024-05-03 | Dev team | Requirements Gathering
|  |  |  | Database setup | 15 days | 2024-05-06 | 2024-05-24 | Dev team | Backend development
|  |  |  | Frontend development | 15 days | 2024-05-06 | 2024-05-24 | Dev team | Backend dev & UI/UX designs
D | TESTING | 40 days | Quality Assurance | Integration testing | 10 | 2024-05-27 | 2024-06-07 | Testers | Back & frontend, database setup
|  |  |  | User Acceptance testing (UAT) | 10 days | 2024-06-10 | 2024-06-21 | Testers | Integration testing
|  |  |  | Bug fixing and optimization | 10 days | 2024-06-24 | 2024-07-05 | Testers | UAT
|  |  | Training | User Training | 5 days | 2024-06-24 | 2024-06-28 | L&D | UAT
|  |  | Deploy | Deployment planning | 5 days | 2024-06-24 | 2024-06-28 | PM | UAT
|  |  |  | Deployment | 5 Days | 2024-07-01 | 2024-07-05 | Dev team | Deployment planning
START
FINISH

## Critical Path
Network Diagram
Activity |  | Task | Immediate Predecessors | Duration
A | 1 | Requirements Gathering | n/a | 5
B | 2 | UI/UX Design | 1 | 10
C | 3 | Backend Dev | 1 | 20
D | 4 | Database setup | 3 | 15
E | 5 | Frontend dev | 2&3 | 15
F | 6 | INT testing | 3,4 & 5 | 10
G | 7 | UAT | 6 | 10
H | 8 | Bug Fixing | 7 | 10
I | 9 | Deploy planning | 7 | 5
J | 10 | Deployment | 9 | 5
LEGEND |  | ITEM | SYMBOL
Ctritical Path
Formula
[5 empty] | ES | ACT | EF
[5 empty] | LS | DUR | LF |  | 5 | B | 15
[9 empty] | 15 | 10 | 25 | 20 | E | 40 |  |  |  | 50 | G | 60 |  | 60 | I | 65
[12 empty] | 25 | 15 | 40 |  |  |  | 50 | 10 | 60 |  | 60 | 5 | 65
[6 empty] | 0 | A | 5 | [6 empty] | 40 | F | 50
[6 empty] | 0 | 5 | 5 | [6 empty] | 40 | 10 | 50
[25 empty] | 65 | J | 70
[25 empty] | 65 | 5 | 70
[19 empty] | 60 | H | 70
[19 empty] | 40 | 10 | 50
[9 empty] | 5 | C | 25 | 25 | D | 40
[9 empty] | 5 | 20 | 25 | 25 | 15 | 40
A
B
C
D
E
F
G
I
H
J
5
10
20
15
15
10
10
10
5
5
START
FINISH

## RISK MATRIX
RISKS
ID | Date Raised | Risk Chategory | Risk Name | Risk Description | Likelihood of risk occuring | Impact if the risk occurs | Severity | Risk owner | Mitigating Action
R001 | 2024-04-09 | Technical Risks | Integration Complexity | Challenges may arise when integrating various systems such as payment gateways, inventory management, and customer relationship management (CRM) tools. | Low | High | High | TBC | Conduct thorough API compatibility checks early in the project. Implement incremental integration and conduct regular testing to identify and address issues promptly.
R002 |  |  | Performance and Scalability | Ensuring the platform can handle peak loads and scale as the business grows. | Low | High | High | TBC | Perform load testing and scalability assessments early in development. Use services that allow for flexible scaling based on demand.
R003 |  |  | Security Vulnerabilities | Risk of data breaches, hacking, or unauthorized access to customer information and payment details. | Low | High | High | TBC | Implement robust security measures such as encryption, regular security audits, and compliance with relevant standards (e.g., PCI-DSS). Conduct penetration testing to identify and mitigate potential weaknesses.
R004 |  | Operational Risks | Dependency on Third-party Services | Reliance on external services (e.g., shipping partners, payment processors) that may have downtime or service interruptions. | Low | High | High | TBC | Identify critical dependencies early. Have contingency plans and alternative providers ready. Implement monitoring and alerting systems for proactive management of service interruptions.
R005 |  |  | Data Integrity and Backup | Risks associated with data loss or corruption, necessitating robust backup and recovery mechanisms. | Low | High | High | TBC | Implement regular automated backups of data. Test backup and recovery procedures to ensure they are reliable and efficient.
R006 |  |  | Compliance and Legal Risks | Adhering to regulations such as POPIA, PCI-DSS for data protection and customer privacy. | Low | High | High | TBC | Be familiar with the requirements and guidelines and adhere to them. These include secure handling of cardholder data, maintaining a secure network, implementing strong access control measures, and regular monitoring and testing of networks.
R007 |  | Business Risks | Market Competition | Launching in a competitive market with established players. | Medium | High | Medium | TBC | Conduct thorough market research to understand competitors, their strengths, weaknesses, and market positioning. Identify gaps or opportunities where your ecommerce platform can differentiate itself.
R008 |  |  | Changing Customer Preferences | Adapting to evolving customer expectations and market trends. | Medium | Medium | Medium | TBC | Regularly solicit and analyze customer feedback through surveys, reviews, and social media interactions. Use data analytics to understand customer behavior and preferences.
R009 |  |  | Financial Risks | Budget overruns, unforeseen costs, and ROI realization challenges. | Low | High | High | TBC | Develop a detailed budget plan that accounts for initial development costs, ongoing operational expenses, marketing campaigns, and contingencies. Monitor expenses closely to avoid budget overruns.
ISSUES
I001 | 2024-04-09 | Internal Issues | Scope Creep | Difficulty in managing evolving requirements and scope changes during sprints. | Low | Medium | Medium | TBC | Use Agile practices like backlog grooming and sprint planning to manage scope changes. Ensure clear communication with stakeholders on the impact of changes and put emphasis on signing off requirements.
I002 |  |  | Resource Constraints | Limited availability of skilled personnel, leading to potential bottlenecks in development or testing. | Medium | High | Medium | TBC | Cross-train team members and invest in skill development. Consider outsourcing or hiring additional resources during peak demand periods.
I003 |  |  | Communication Breakdown | Misalignment between stakeholders, developers, and users regarding project goals, features, or expectations. | High | High | High | TBC | Foster a culture of open communication and transparency. Conduct regular meetings, such as daily stand-ups and sprint reviews, to ensure everyone is aligned on project goals and progress.
ASSUMPTIONS
A001 | 2024-04-09 | Assumptions | Stable Technology Stack | Assuming the chosen technologies and frameworks will support the required functionalities without significant technical limitations or unforeseen issues. | Low | High | Medium | TBC | Conduct proof of concept and feasibility studies before committing to technologies. Stay updated with technology trends and have contingency plans for technology changes if necessary.
A002 |  |  | User Adoption | Assuming that users will easily adapt to the new platform and its features, without significant resistance or usability issues. | Low | High | Medium | TBC | Involve users in the development process through user testing and feedback sessions. Provide training and support materials to facilitate smooth adoption. For end users, use social media to create 'How to' videos that will be posted on our channels.
A003 |  |  | Availability of Resources | Assuming that necessary resources (budget, personnel, infrastructure) will be available throughout the project lifecycle. | Low | High | Medium | TBC | Regularly monitor resource utilization and budget expenditures. Have contingency plans in place for unexpected resource shortages or budget constraints.
DEPENDENCIES
D001 | 2024-04-09 | Dependencies | External Services and APIs | Dependence on third-party APIs (e.g., payment gateways, shipping APIs) for key functionalities. | Low | High | Medium | TBC | Establish SLAs with service providers. Have backup plans and alternative providers identified in case of API changes or service disruptions.
D002 |  |  | Team Collaboration | Dependencies on cross-functional teams (e.g., development, UX/UI design, marketing) for integrated product delivery. | Medium | High | Medium | TBC | Use Agile ceremonies like daily stand-ups, sprint planning, and retrospectives to facilitate communication and collaboration. Encourage cross-functional training and knowledge sharing.
D003 |  |  | Regulatory Compliance | Dependencies on legal and compliance requirements, which may influence feature development and deployment timelines. | Low | High | Medium | TBC | Stay informed about relevant regulations and ensure compliance throughout the development process. Involve legal and compliance experts in project planning and execution.